Valley ROP Teacher Website Implementation Plan

| IMPLEMENTATION | EVALUATION |
| --- | --- |
| **What needs to be done?** | **By when?** | **What resources?** | **What evidence indicates this progress?** | **How and when will evidence be gathered?** |
| Start a Google Website or a Learning Management System (LMS) | February 5th, 2016 | 2016 Spring In-ServiceWebsite workshop and Valley ROP Website | Fill up the Google Form indicating the website URL Link | February 5th, 2016 |
| Create the following action on your website:* Upload your class Syllabus
* Teacher Bio
* Welcome Statement Teacher Contact Info – email and school number
* Create New Pages and Edit Side bar
 | February 5th, 2016 | 2016 Spring In-ServiceWebsite workshop and Valley ROP Website | Fill up the Google Form indicating the website URL Link | February 5th, 2016 |
| Create the following action on your website:* Organize by subject/class
* Subject/Class Description
* Pathway Information (VROP Website)
* PDFs for study guides, permissions slips, handouts, Forms etc.
* Informal goals for the year
 | 2016 Fall In-service  | 2016 Fall In-ServiceWebsite workshop and Valley ROP Website | URL will be linked to Valley ROP Webpage | November 2016 |
| Create the following action on your website:* Share lessons
* PowerPoint
* Chapter Review, etc.
* Class Assignments
* Bonus assignments
 | 2016 Fall In-service | 2016 Fall In-ServiceWebsite workshop and Valley ROP Website | URL will be linked to Valley ROP Webpage | November 2016 |
| Create the following action on your website:* Educational videos
* Online tutorials
* Photos of your classroom
* And probably lots more
 | 2017 Spring In-service | 2017 Spring In-ServiceWebsite workshop and Valley ROP Website | URL will be linked to Valley ROP Webpage | Spring 2017 |